## Sheet1
Project Loz & Liv
Task Name | Start | Duration (days)
Stripping out tiles, basin,toilet, towel rail, bath | 2017-02-07 | 1
dumping at tip | 2017-02-08 | 0.5
confirm layout | 2017-02-08 | 1
move pipes | 2017-02-09 | 1
soil pipe work | 2017-02-10 | 1
temp waste path | 2017-02-11 | 1
repair walls | 2017-02-07 | 0
tiling | 2017-02-07 | 0
Fitting of sink, wc, radiator | 2017-02-18 | 1
plumb furniture | 2017-02-19 | 1
repaint ceiling and walls | 2017-02-07 | 0
Task 12 | 2017-02-07 | 0

## Sheet2
Stripping out tiles, basin,toilet, towel rail, bath
dumping at tip
confirm layout
move pipes
soil pipe work
temp waste path
repair walls
tiling
Fitting of sink, wc, radiator
plumb furniture
repaint ceiling and walls